## Product Backlog
PLANNED SPRINT | ACTUAL SPRINT | USER ID | USER STORY DESCRIPTION | ESTIMATE | MOSCOW | DEPENDENCY | ASSIGNEE | STATUS
Sprint 1 | Sprint 1 | SCRUM-2 | As a user , I want to securely login to the system and for any invalid detail , i want to see a proper alert indicating that error. | 0.05 hrs | Must Have | NA | Aman Garg | Done
Sprint 1 | Sprint 1 | SCRUM-4 | As a user, I want to search for flights and validate the test cases in each specific scenarios. | 0.20 hrs | Must Have | NA | Chirag Guruswamy | Done
Sprint 1 | Sprint 1 | SCRUM-5 | As a user, I want to submit an enquiry and receive confirmation, with alerts shown for any invalid or missing input. | 0.25 hrs | Must Have | NA | Sakshi | Done
Sprint 1 | Sprint 1 | SCRUM-3 | As a user, I want to book a flight ticket. | 0.25 hrs | Must Have | NA | Arghyadip Santra | Done

## Sprint Backlog
USER ID | TASK ID | TASK DESCRIPTION | TEAM MEMBER | ACTIVITY | STATUS
SCRUM -2 | SCRUM-6 | Design and Execute Manual Test Cases | Aman Garg | Test Case Design and Test Case Exceution | Done
SCRUM -2 | SCRUM-7 | Validate Test Results and Prepare Test Reports | Aman Garg | Validate Results and Prepare Reports | In progress
SCRUM -4 | SCRUM-10 | Design & Execute Manual Test Cases for Flight Search Module | Chirag Guruswamy | Test Case Design and Test Case Exceution | Done
SCRUM -4 | SCRUM-11 | Validate Test results and Prepare Report Data for Flight Search Module | Chirag Guruswamy | Validate Results and Prepare Reports | Done
SCRUM-5 | SCRUM-12 | Design & Execute Manual Test Cases for Enquiry Module | Sakshi | Test Case Design and Test Case Exceution | Done
SCRUM-5 | SCRUM-13 | Validate Test Results and Prepare Report for Enquiry Module | Sakshi | Validate Results and Prepare Reports | In progress
SCRUM -3 | SCRUM-8 | Design & Execute Manual Test Cases for Ticket Booking Module | Arghyadip Santra | Test Case Design and Test Case Exceution | Done
SCRUM -3 | SCRUM-9 | Validate Results and Prepare Report for Ticket Booking Module | Arghyadip Santra | Validate Results and Prepare Reports | Done

## Tracebility Matrix
USER STORY ID | TEST CASE ID | AUTOMATED | DEFECT ID
SCRUM -2 | SCRUM-T1 | NO | NA
SCRUM-2 | SCRUM-T2 | NO | SCRUM-15
SCRUM-2 | SCRUM-T3 | NO | SCRUM-14
SCRUM-5 | SCRUM-T10 | NO | SCRUM-18
SCRUM-5 | SCRUM-T11 | NO | NA
SCRUM-5 | SCRUM-T12 | NO | NA
SCRUM -3 | SCRUM-T4 | NO | NA
SCRUM -3 | SCRUM-T5 | NO | NA
SCRUM -3 | SCRUM-T6 | NO | NA
SCRUM -4 | SCRUM-T7 | NO | SCRUM-21
SCRUM -4 | SCRUM-T8 | NO | SCRUM-22
SCRUM -4 | SCRUM-T9 | NO | NA
SCRUM-4 | SCRUM-T15 | NO | SCRUM-24
SCRUM-4 | SCRUM-T16 | NO | NA
SCRUM-2 | SCRUM-T17 | NO | NA
SCRUM-2 | SCRUM-T18 | NO | SCRUM-23
SCRUM-5 | SCRUM-T13 | NO | NA
SCRUM-5 | SCRUM-T14 | NO | NA
SCRUM -3 | SCRUM-T19 | NO | NA
SCRUM -3 | SCRUM-T20 | NO | NA

## Test Execution Report
TEST CASE ID | TEST SCENARIO | RESULT | EXECUTION DATE | EXECUTED BY
SCRUM-T1 | Validate successful login with valid credentials | PASS | 2025-06-25 | Aman Garg
SCRUM-T2 | Validate login with incorrect password | FAIL | 2025-06-25 | Aman Garg
SCRUM-T3 | Validate login with empty username field | FAIL | 2025-06-26 | Aman Garg
SCRUM-T11 | Validate error for invalid email format | PASS | 2025-06-26 | Sakshi
SCRUM-T7 | Validate successful flight search by valid Flight Number | FAIL | 2026-06-26 | Chirag Guruswamy
SCRUM-T8 | Validate search for a non-existent Flight Name | FAIL | 2026-06-26 | Chirag Guruswamy
SCRUM-T9 | Validate search with empty search criterion input | PASS | 2026-06-26 | Chirag Guruswamy
SCRUM-T12 | Validate error when Name field is left empty | PASS | 2025-06-26 | Sakshi
SCRUM-T10 | Validate successful enquiry submission with valid data | FAIL | 2025-06-26 | Sakshi
SCRUM-T4 | Validate successful flight booking with valid data | PASS | 2025-06-26 | Arghyadip Santra
SCRUM-T5 | Validate error when Travel From and Travel To are the same | FAIL | 2025-06-26 | Arghyadip Santra
SCRUM-T6 | Validate error for past travel date | FAIL | 2025-06-26 | Arghyadip Santra
SCRUM-T15 | Validate search with special characters in Flight Name | FAIL | 2025-06-30 | Chirag Guruswamy
SCRUM-T16 | Validate flight search with partial Flight Name | PASS | 2025-06-30 | Chirag Guruswamy
SCRUM-T18 | Validate login with correct details and empty captcha field | FAIL | 2025-06-30 | Aman Garg
SCRUM-T17 | Validate login with correct details and incorrect captcha | PASS | 2025-06-30 | Aman Garg
SCRUM-T14 | Validate Error When All Fields Are Empty | PASS | 2025-07-01 | Sakshi
SCRUM-T13 | Validate Error When Message Field is Empty | PASS | 2025-07-01 | Sakshi
SCRUM-T19 | Validate flight booking in every class | PASS | 2025-07-02 | Arghyadip Santra
ScrUM-T20 | Valifdate flight booking with invalid phone no | FAIL | 2025-07-02 | Arghyadip Santra

## Bug Report
BUG ID | SUMMARY | SEVERITY(Low,Medium,High) | STATUS | LINKED TEST CASE | REPORTED BY | SPRINT
SCRUM-14 | Upon correct password and empty username , it displays :wrong password alert too instead of only "empty username alert". | Low | Unresolved | Scrum - T3 | Aman Garg | Scrum Sprint 1
SCRUM-15 | Upon incorrect password and correct username , it displays :wrong username alert too instead of only "incorrect password alert". | Low | Unresolved | Scrum-T3 | Aman Garg | Scrum Sprint 1
SCRUM-18 | Enquiry form retains previous input after clicking Submit; fields are not cleared. | Low | Unresolved | SCRUM-T10 | Sakshi | Scrum Sprint 1
SCRUM-16 | No error when Destination from and Destination To are same | Low | Unresolved | Scrum - T2 | Arghyadip Santra | Scrum Sprint 1
SCRUM-17 | No error Booking shown while booking flight in Previous date | Medium | Unresolved | Scrum - T2 | Arghyadip Santra | Scrum Sprint 1
SCRUM-21 | System does not display a message 'No flights found matching your criteria' when searched. | Low | Unresolved | Scrum-T4 | Chirag Guruswamy | Scrum Sprint 1
SCRUM-22 | Valid flight search using Flight Number does not display flight details. | High | Unresolved | Scrum-T4 | Chirag Guruswamy | Scrum Sprint 1
SCRUM-23 | Validate login with correct details and empty captcha field | Medium | Unresolved | Scrum-T3 | Aman Garg | Scrum Sprint 1
SCRUM-24 | Flight search fails when special characters are entered in Flight Name | Low | Unresolved | Scrum-T4 | Chirag Guruswamy | Scrum Sprint 1
SCRUM-25 | Flight Booking with invalid phone no. | Medium | Unresolved | Scrum - T2 | Arghyadip Santra | Scrum Sprint 1

## Test Cases
TEST SCENARIO | STEPS | EXPECTED RESULT | FINAL STATUS
Validate login with empty username field | Leave username field empty , Enter valid password ,Click 'Login' button | An error message 'Please enter username' is displayed below the username field. | FAIL
Validate login with empty username field | Enter valid username, Enter invalid password ,Click 'Login' button | An error message 'Invalid credentials' is displayed on the login page. | FAIL
Validate login with empty username field | Enter valid username,Enter valid password ,Click 'Login' button | User is redirected to the Dashboard page, 'Welcome!' message displayed. | PASS
Validate search for a | Step 1:Select 'Flight Name' as search criterion | A message 'No flights found matching your criteria' should be displayed. | FAIL
non-existent Flight Name | Step 2:Enter a flight name that does not exist in the system
Step 3:Click 'Search' button
Validate search with empty search criterion input | Step 1:Select any search criterion (e.g., Flight Number) | An error message 'Please enter search criteria' or similar is displayed, or no search is performed. | PASS
Step 2:Leave the search input field empty
Step 3:Click 'Search' button
Validate successful flight search by valid Flight Number | Step 1:Select 'Flight Number' as search criterion | Details of Flight FL101 are displayed in the search results. | FAIL
Step 2:Enter a valid existing Flight Number
Step 3:Click 'Search' button
Validate error for invalid email format | Step 1:Enter valid Name and Message | An error message 'Please enter a valid email address' is displayed below the email field. | PASS
Step 2:Enter an email with an invalid format
Step 3:Click 'Submit' button
Validate error when Name field is left empty | Step 1:Leave Name field empty | An error message displayed below the name field:- Your name should be at least 3 characters long. | PASS
Step 2:Enter valid Email and Message
Step 3:Click 'Submit' button
Validate successful flight booking with valid data | Step1: Fill all mandatory fields with valid data Step2:Click 'Submit' button Step3:Verify booking details are correctly displayed. | All fields accept valid input; A confirmation page or message indicating successful booking is displayed ; Displayed booking details match the entered data. | PASS
Validate successful enquiry submission | Step 1:Enter valid Name, Email, Phone Number, Subject and Message | Name, Email, Phone Number, Subject and Message fields are empty, ready for new input. | FAIL
with valid data | Step 2:Click 'Submit' button
Step 3:Verify fields are cleared after submission
Validate error when Travel From and Travel To are the same | Step 1:Select same locations for 'Travel From' and 'Travel To' Step 2:Fill other mandatory fields with valid data Step 3: Click 'Submit' button | Both dropdowns accept the same location ; Other fields accept valid input ; An error message 'Travel From and Travel To cannot be the same' is displayed. | FAIL
Validate error for past travel date | Step 1: Fill valid data for all fields except 'Date' Step 2: Select a date in the past Step 3: Click 'Submit' button | Fields accept valid inputs ; An error message 'Travel date cannot be in the past' is displayed. | FAIL
Validate login with correct details and incorrect captcha | Fill valid data for username and password field. Enter incorrect data for captchaand Click on Validate. | An error message showing invalid captch amust be seen | PASS
Validate login with correct details and empty captcha field | Fill valid data for username and password field.Leave empty captcha field and Click on Validate. | An error message must be shown saying "enter captcha" | FAIL
Validate Flight Booking in Every Class | Fill select class as Luxury Class , Economic class, First class. | Fields accept valid inputs, No error occurs | PASS
Validate flight Booking with invalid phone no | Fill Invalid phone no | An error message 'Invalid phone no' is displayed on the ticket booking page. | FAIL
Validate Error When Message Field is Empty | Step 1:Open the enquiry form | Error: "Message field is required" | PASS
Step 2:Enter Name
Step 3:Enter Email
Step 4:Leave the Message field empty
Step 5:Click Submit
Validate Error When All Fields Are Empty | Step 1:Open the enquiry form | "Name field is required" | PASS
Step 2:Leave all fields blank
Step 3:Click Submit
Validate search with special characters in Flight Name | Step 1:Go to Flight Search | Application shows “No results found” or handles input. | FAIL
Step 2:Enter @#% in the Flight Name field
Step 3:Click Search for Flight
Validate flight search with partial Flight Name | Step 1:Go to Flight Search page | Flights with "Sky" in their names are displayed in the results table | PASS
Step 2:Enter "Sky" in the Flight Name fiel
Step 3:Click Search for Flight